## PLAN PROJEKTA
| Predviđanje svojstava molekula |  |  |  |  | Početak projekta: | [7 empty] | 2024-10-21
[6 empty] | Tjedan: | [7 empty] | 6
[6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30 | [6 empty] | 2025-01-06 | [6 empty] | 2025-01-13
| ZADATAK | NAPREDAK | POČETAK | KRAJ | time axis 2024-11-25 to 2025-01-19
 | time axis 2024-11-25 to 2025-01-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Inicijalni koraci
| Definicija teme | 100% | 2024-10-21 | 2024-10-25 | 5
| Istraživanje stručne literature | 80% | 2024-10-25 | 2024-11-19 | 26
| Izrada plana projekta | 100% | 2024-10-25 | 2024-11-10 | 17
Rad na projektu
| Odabir podatkovnog skupa | 0% | 2024-11-20 | 2024-11-23 | 4
| Priprema podataka | 0% | 2024-11-24 | 2024-12-03 | 10
| Obrada podataka | 0% | 2024-12-03 | 2024-12-13 | 11
| Istraživanje modela | 0% | 2024-12-13 | 2024-12-17 | 5
| Implementacija i treniranje modela | 0% | 2024-12-17 | 2025-01-06 | 21
Evaluacija i interpretacija
| Evaluacija modela | 0% | 2025-01-07 | 2025-01-14 | 8
| Interpretacija rezultata i nalazak ključnih svojstava | 0% | 2025-01-07 | 2025-01-14 | 8
Završna faza
| Završetak plana projekta | 0% | 2025-01-15 | 2025-01-20 | 6
| Izrada projektne dokumentacije | 0% | 2024-11-24 | 2025-01-20 | 58
Insert new rows ABOVE this one